NIAID-BRC AI Codeathon 2026 — Project Proposal Template

Event website: https://niaid-brc-codeathons.github.io/

Project Title

Hypothesis2Omics: Agentic Multi-Omics Validation

Project Theme [Check One]

☐ Automated Knowledge Extraction and Curation

☒ Automated Workflow Generation and Execution

☐ Both

Team Name: Hypothesis2Omics

Team Lead(s):

- Lead 1: Slim Fourati — Northwestern University

- Lead 2: Rushikesh Lagad — University of Arkansas

Team Members and Roles [6-10 members]

| Name | Affiliation | Role / Expertise |
| --- | --- | --- |
| Slim Fourati | Northwestern University | Project Lead / Bioinformatics |
| Rushikesh Lagad | University of Arkansas | Project Lead / Bioinformatics |
| Amar Kumar | University of Illinois Chicago | Member / Data analysis |
| Melanie Sadecki | North Carolina State University | Member / |
| Yaphet Kebede | RENCI, University of North Carolina at Chapel Hill | Member / RAG |
| Yijun Zhou | NIAID Vaccine Production Program | Member / Biochem + Programming |
| Yonglan Liu | NIAID / NIH | Member / |
| Archit Vasan | BV-BRC, Argonne National Laboratory | BV-BRC/ANL support / Agentic system for Protein design |

Project Summary

Public omics repositories contain many datasets that could test infectious-disease and vaccine hypotheses, but identifying suitable studies, assessing whether their design and metadata are adequate, and reproducing analyses remain highly manual. Hypothesis2Omics will develop an AI-agent prototype that converts a biological hypothesis into explicit eligibility criteria and statistical tests, discovers relevant public transcriptomic and related omics datasets, and determines which studies can validly address the question. For eligible studies, the agent will configure and execute reproducible workflows through BRC Analytics, capture provenance, and compare results across independent datasets. The minimal viable product (MVP) will focus on one predefined vaccination hypothesis, such as the role of GCN2 in CD8+ T cell response in yellow fever vaccination [Rodrigues-Coffinet L. et al. 2025 Sciences Immunol]. The final output will be a provenance-linked evidence table that classifies each transcriptomic dataset as supportive, contradictory, or inconclusive and provides a calibrated overall assessment.

Goals and Objectives

During the Codeathon, the team will pursue the following measurable goals:

- Goal 1: Convert one predefined hypothesis into a structured test specification, search strategy, and explicit dataset inclusion/exclusion criteria.

- Goal 2: Identify and adjudicate candidate public datasets, then reproducibly execute an appropriate workflow on at least one and ideally 2–3 independent eligible datasets.

- Goal 3: Integrate cross-dataset results into an auditable evidence table and benchmark retrieval, eligibility decisions, workflow success, and agreement with published findings.

Approach

- Methods: LLM-based agent orchestration with tool/API calls for repository search, metadata extraction, eligibility reasoning, workflow configuration, execution, statistical quality control, and evidence synthesis.

- Milestones: (1) formalize hypothesis; (2) discover/rank datasets; (3) assess eligibility; (4) configure and run BRC Analytics workflows; (5) harmonize effect estimates and perform robustness checks; (6) generate the final evidence report.

Workflow: Biological hypothesis → Test specification → Dataset discovery → Eligibility assessment → Workflow execution → Statistical/scientific critique → Cross-dataset synthesis → Evidence report.

Data and Resources Required

| Resource Type | Source / Link | Description / Purpose |
| --- | --- | --- |
| Data | GEO (GSE125921, GSE136163, GSE13485, GSE82152, GSE13699), ImmPort (SDY1529, SDY1264, SDY1294, SDY1289), NIAID BRC resources | Candidate transcriptomic/immune datasets and study metadata for hypothesis testing and independent replication. |
| Tools / Services | BRC Analytics; repository APIs; R/Python; MCP services | Dataset retrieval, metadata parsing, workflow execution, differential/pathway analysis, provenance capture, and result harmonization. |
| LLM/AI Models | Codeathon-provided LLM access | Natural-language hypothesis formalization, agent planning, metadata reasoning, tool selection, workflow configuration, and evidence synthesis. |
| Compute and Storage Needs | BRC/Argonne compute infrastructure; modest temporary storage | Execution of selected workflows and storage of intermediate results, logs, provenance, and final evidence tables. |

Expected Outcomes / Deliverables

By the end of the Codeathon, the team expects to deliver:

- A working end-to-end prototype that accepts a predefined biological hypothesis and produces a structured test plan.

- A ranked dataset inventory with explicit eligibility decisions, inclusion/exclusion reasons, and provenance.

- Reproducible workflow configurations and analysis outputs for at least one, ideally multiple, eligible public datasets.

- A cross-dataset evidence table/report plus an integration concept for BRC Analytics, and future multi-omics or microbiome MCP tools.

Potential Impact and Next Steps

Hypothesis2Omics will demonstrate how AI agents can turn public biomedical data into reproducible, testable evidence rather than only generate narrative answers. The project can accelerate infectious-disease and vaccine research by reducing the time required to locate appropriate cohorts, verify study suitability, and reproduce analyses across independent datasets. Its emphasis on explicit eligibility criteria, provenance, robustness, and an “inconclusive” outcome improves interpretability and reduces overclaiming. After the Codeathon, the framework can be expanded to proteomics, metabolomics, microbiome, single-cell, and immune-profiling data, with formal meta-analysis, causal-inference modules, and continuous re-evaluation as new public datasets become available.

- Infectious disease research: faster reuse of public datasets to validate vaccine and host-response hypotheses across cohorts.

- AI/ML automation and interpretability: auditable agent decisions, reproducible workflows, and provenance-linked evidence synthesis.

- Public health preparedness: rapid re-analysis of existing data when new pathogens, variants, biomarkers, or intervention questions emerge.

Next steps: benchmark against expert-curated searches and published analyses; expand repository and omics coverage; add formal meta-analysis and microbiome causal-inference tools; and package the framework for reusable BRC deployment.

Technical Support Needed

Indicate additional requirements:

☒ Datasets preloaded (helpful for MVP benchmark datasets)

☒ GPU / LLM access

☒ API keys / repository and workflow-service access as needed

☒ Mentor support (BRC Analytics, Galaxy, APIs, and workflow integration)

☒ Other: access to BRC Analytics execution endpoints and provenance/logging support

Additional Comments

MVP scope will prioritize one vaccination hypothesis and one primary omics modality. The prototype should find appropriate datasets, reject unsuitable ones, execute a valid analysis, and report supportive, contradictory, or insufficient evidence without overinterpretation.